## Milestones
News Synthesis & Credibility Engine — Milestone Tracksheet
Update this every working session. Status values: Not started / In progress / Blocked / Done. Keep the Change Log tab in sync.
ID | Milestone | Phase | Stage Doc | Definition of Done | Status | Notes / Date
M0 | Golden dataset | Setup | STAGE_0_GOLDEN_DATASET.md | 8–12 articles for 1 event saved with metadata; both beats configured (stub) | Done | Event: Netanyahu 70% Gaza announcement (2026-05-28). 10 articles, 5 full text + 5 metadata-only. 2026-05-31
M1 | Ingest | 1 | STAGE_1_INGEST.md | Pipeline pulls articles for a beat into stored raw form (schema matches golden); dedup works | Done | RSS ingester + dedup/store + CLI runner built. All 10 israel_middle_east sources wired. Schema round-trip + dedup verified. 2026-05-31
M2 | Cluster | 1 | STAGE_2_CLUSTER.md | Articles auto-grouped into event clusters; golden event reconstructed correctly | Done | pipeline/cluster/ built: embed.py (sentence-transformers), group.py (cosine threshold + connected components, manual override), run.py (CLI). 2026-05-31
M3 | Analyze | 1 | STAGE_3_4_ANALYZE_ANNOTATE.md | Per-event JSON: claims-by-source + consensus/divergence classification for golden event | Done | pipeline/analyze/ built and verified: extract.py (Haiku), reconcile.py (Sonnet), run.py (CLI). Output: 32 reconciled claims (21 agreed, 2 contested, 9 single_source). Written to evt_2026_05_31_001_analyzed.json. 2026-05-31
M4 | Annotate | 1 | STAGE_3_4_ANALYZE_ANNOTATE.md | Provenance cards + per-claim rationale written into the per-event JSON | Done | pipeline/annotate/ built and verified: provenance.py (outlet ownership cache + Haiku author lookup), run.py (CLI). All 10 sources annotated; 1 named author background filled (Simon Speakman Cordall / Al Jazeera). Updated analyzed JSON in-place. 2026-05-31
M5 | Phase-1 page | 1 | STAGE_6_FRONTEND.md (Pass A) | Next.js page renders annotated analysis for the golden event | Done | Next.js app built in web/. Event page with BiasLegend, collapsible ClaimSection, ClaimCard with expand/collapse, SourceCard. UI fixes applied: light-mode locked, bias legend, collapsible groups, outlet+date display. Run: cd web && npm install && npm run dev. 2026-05-31
M6 | Validate Phase 1 | 1 | — (user testing) | Spectrum-spanning readers say the analysis is fair and useful | In progress | Internal content audit done (Session 3). External validation pending (G to run). Known data bugs left for pipeline re-run (B-01, B-02). Kept open for future fine-tuning. 2026-06-01
M7 | Generate | 2 | STAGE_5_GENERATE.md | Report written into JSON, grounded in + linked to claims/sources | Done | pipeline/generate/ built and run. 11 paragraphs generated (agreed/contested/framing/background), all claim_id/source_id references validated. report field written to evt_2026_05_31_001_analyzed.json. 2026-06-01
M8 | Toggle UI | 2 | STAGE_6_FRONTEND.md (Pass B) | Report-by-default page; per-paragraph expandable receipts via the toggle | Done | ReportView component built: continuous sidebar bar (kind-colored), transparency toggle (indigo pill), per-paragraph Show/Hide sources, kind tags with hover tooltips, pale source chips, bullet points for claims. 2026-06-01
M9 | Validate Phase 2 | 2 | — (user testing) | Readers find the synthesis fair; 20–30 events processed | In progress | 2026-06-01 — Scale test runner written (scripts/scale_test.py). B-01/B-02 enforced in reconcile.py. Awaiting G to run --discover and --run-events locally.

## Change Log
Change Log
Append a row whenever something changes: a milestone status, an architecture decision, a schema version, a source list, etc. Newest at the bottom.
Date | Milestone / Area | What changed | Why | By
2026-05-31 | Project setup | Master document, per-stage instruction docs, and this tracksheet created | Establish a legible, handover-ready project structure for Claude Code/Cowork | G + Claude
2026-05-31 | Architecture | Adopted hybrid model: Ingest→Cluster→Analyze→Annotate→Generate, with annotations preserved and surfaced | Annotation layer is what earns reader trust in the generated report | G + Claude
2026-05-31 | Tech decision | Pipeline = Python; Front end = Next.js (React); artifact = per-event JSON on disk | Reuse Deep Research Reporter; localhost-now-no-rewrite-later; clean pipeline/UI separation | G + Claude
2026-05-31 | Beats | Primary = Israel/Middle East; Secondary = General world news; beats are config not code | Deepest source instincts on primary; prove generalization on secondary | G + Claude
2026-05-31 | Schema | Per-event JSON schema v0.1 defined in STAGE_3_4 | Establish the contract between pipeline and front end | G + Claude
2026-05-31 | M0 — Repo scaffold | Created directory structure: docs/, config/beats/, data/golden/, data/ingested/, data/events/, pipeline/, web/. Added .gitignore and .env.example. | Required by HANDOVER §7 before golden dataset work | Claude (Cowork)
2026-05-31 | M0 — Golden dataset | Selected event: Netanyahu 70% Gaza territorial control announcement (2026-05-28). 10 articles spanning left (Al Jazeera x2, Truthout, Democracy Now), center (Reuters, Euronews, Bloomberg), center-left (Haaretz), center-right (Times of Israel, JNS). Saved to data/golden/event_001/. | M0 definition of done met | Claude (Cowork)
2026-05-31 | M0 — Beat configs | Stubbed config/beats/israel_middle_east.json (10 sources + GDELT query) and world_news.json (8 sources). | Required by STAGE_0 definition of done | Claude (Cowork)
2026-05-31 | M1 — Ingest | Built pipeline/schema.py (Article dataclass), pipeline/ingest/rss.py (feedparser + trafilatura), pipeline/ingest/store.py (URL-normalised dedup + storage), pipeline/ingest/run.py (CLI). All 10 israel_middle_east sources wired from beat config. Schema round-trip and dedup verified. | M1 definition of done met | Claude (Cowork)
2026-05-31 | M2 — Cluster | Built pipeline/cluster/embed.py (sentence-transformers all-MiniLM-L6-v2, L2-normalised), group.py (threshold-based cosine similarity + connected components; manual override), run.py (CLI: --source golden/live, --threshold, --manual). Outputs cluster JSON to data/events/<beat>/. | M2 definition of done met — auto-cluster + manual override ready; correctness check runs against golden event_001 | Claude (Cowork)
2026-05-31 | M3 — Analyze | Built pipeline/analyze/: extract.py (Haiku per-article claim extraction), reconcile.py (Sonnet cross-article consensus/divergence), run.py (CLI runner). Outputs per-event JSON v0.1 with claims classified as agreed/contested/single_source. Ready to run locally against golden event_001. | M3 pipeline code complete — API calls require local Python (sandbox outbound HTTPS blocked) | Claude (Cowork)
2026-05-31 | M3 — Analyze DONE | pipeline/analyze/run.py executed successfully against golden event_001. 138 raw claims → 32 reconciled (21 agreed across spectrum, 2 contested, 9 single_source). Per-event JSON v0.1 written to data/events/israel_middle_east/evt_2026_05_31_001_analyzed.json. json-repair added as dep. | M3 definition of done met | Claude (Cowork)
2026-05-31 | M4 — Annotate DONE | pipeline/annotate/run.py executed. Ownership filled for all 10 sources from curated cache (data/sources/outlet_provenance.json). Author background filled for 1 named byline (Simon Speakman Cordall, Al Jazeera). Author cache written to data/sources/author_cache.json. evt_2026_05_31_001_analyzed.json updated in-place. | M4 definition of done met | Claude (Cowork)
2026-05-31 | M5 — Phase-1 page DONE | Next.js app scaffolded in web/. Components: BiasLegend (spectrum bar + outlet placement), ClaimSection (collapsible groups), ClaimCard (expandable rationale + framing), SourceCard (provenance). Data loaded from analyzed JSON via lib/data.ts. | M5 definition of done met | Claude (Cowork)
2026-05-31 | UI — Light mode locked | Disabled dark mode (removed prefers-color-scheme media query, set color-scheme: light on html). Typography floor defined: gray-600 = body min, gray-500 = absolute floor, gray-400 = metadata only. Alternatives logged in Master Doc §12. | Dark mode caused sub-WCAG contrast on system dark backgrounds | G + Claude (Cowork)
2026-05-31 | UI — Bias color legend | Added BiasLegend component: gradient bar (blue→sky→gray→orange→red) with event outlets placed at their spectrum positions. Appears above claims section. Rationale and alternatives logged in Master Doc §12. | Colors were meaningful but unexplained to readers | G + Claude (Cowork)
2026-05-31 | UI — Source attribution | All internal IDs (src_001 etc.) replaced with "Outlet · Date" display. Date format uses device locale (toLocaleDateString). Logged in Master Doc §12. | Internal IDs should never be reader-visible | G + Claude (Cowork)
2026-05-31 | UI — Bias legend UX | Moved BiasLegend inside "What the coverage shows" section. Removed background card styling (blends with page). Left-aligned outlet names. Separated from header area. | Legend felt disconnected from the claims it describes; card bg conflicted with dark-mode body | G + Claude (Cowork)
2026-05-31 | UI — Claim groups default closed | Changed ClaimSection defaultOpen from true to false. All three groups (Agreed/Contested/Single-source) now collapsed on page load. | Page was overwhelming on open; reader should choose what to expand | G + Claude (Cowork)
2026-05-31 | UI — Count replaces dot | Replaced colored dot in ClaimSection header with the numeric count of claims in that group (colored to match the accent). | Dot conveyed no information; the number is more immediately useful | G + Claude (Cowork)
2026-06-01 | M6 — Validate Phase 1 | Status set to In progress. Internal content audit complete (Session 3); external validation pending. Known data bugs (clm_015 src_004 dupe, clm_016/024 agreed-without-spectrum) left for next pipeline re-run. M6 kept open for future fine-tuning per G decision. | G decided to move to M7 without waiting for external validation — M6 remains a living checkpoint | G + Claude (Cowork)
2026-06-01 | M7 — Generate | pipeline/generate/ created. generate.py: GENERATE_SYSTEM prompt instructs Sonnet to write 10-14 paragraphs (kinds: agreed/contested/framing/background) strictly grounded in the claim inventory; claim_id + source_id references required per paragraph; no hallucination. run.py: CLI loads _analyzed.json, calls generate_report(), validates all cited IDs, writes report field in-place. --force flag to regenerate. | M7 started — pipeline code complete, syntax-checked; G to run locally against golden event_001 | Claude (Cowork)
2026-06-01 | M7 — Generate DONE | pipeline/generate/run.py executed locally. 11 paragraphs generated by Sonnet and written to report field in evt_2026_05_31_001_analyzed.json. All cited claim_ids and source_ids validated clean. | M7 definition of done met | G + Claude (Cowork)
2026-06-01 | M8 — Toggle UI | Started. Building report-first page with per-paragraph expandable claim receipts. | M8 started | Claude (Cowork)
2026-06-01 | M8 — Toggle UI DONE | ReportView built in web/components/ReportView.tsx. Features: continuous 2px sidebar bar colored by paragraph kind (agreed=green, contested=amber, framing=indigo, background=slate); indigo pill transparency toggle; per-paragraph Show/Hide sources button; kind tags (Agreed/Contested/Framing/Background) visible only in transparency mode with hover tooltips; supporting claims rendered as bullet points; outlet chips use pale tinted colors; duplicate outlet deduplication in receipts. | M8 definition of done met | Claude (Cowork)
2026-06-01 | M7 — Generate prompt improvements | GENERATE_SYSTEM prompt updated with 4 new rule sections: (1) Source balance — weight by ideological breadth not source count; (2) Quotes — include verbatim first-person quotes from framing_variants where available; (3) Casualty figures — attribute Gaza death toll to Hamas-run Gaza Health Ministry; (4) Regional conflict context — explain Hezbollah/Iran proxy background when Lebanon/Syria operations are mentioned. Report regenerated with --force: 11 paragraphs. | Addresses reviewer feedback on imbalance, missing context, sourcing transparency, and quote density | G + Claude (Cowork)
2026-06-01 | Schema / Data — B-07 identified | clm_024 (total death toll >72,000) is classified agreed but both supporting sources are Al Jazeera English articles (same outlet). Should be single_source. Left for automated fix on next pipeline re-run via B-01 enforcement. Noted in Master Doc §13 as B-07. | Reviewer flagged the claim appearing in Agreed section despite single-outlet sourcing | G + Claude (Cowork)
2026-06-01 | B-01/B-02 — reconcile.py enforcement | Added enforce_classification_rules(): auto-reclassifies "agreed" → "corroborated" when cross-spectrum diversity is absent (B-01); removes source overlap from contested_by (B-02). Previously these were warnings only. | Fixes clm_016, clm_024, clm_015 misclassifications on next pipeline re-run | Claude (Cowork)
2026-06-01 | M3 — analyze/run.py article lookup fix | load_articles_cluster() now searches data/ingested/<beat>/ for live-ingested articles. Previously only searched golden and a legacy path — blocking the scale test. | Pipeline would silently skip all articles on live cluster runs | Claude (Cowork)
2026-06-01 | M9 — Scale test runner | scripts/scale_test.py written. --discover: ingest + cluster, print event list with outlet diversity. --run-events id1,id2: full pipeline (analyze → annotate → generate) for each event, prints localhost URLs. | M9 scale test now runnable with two commands | Claude (Cowork)
2026-06-01 | M9 — Validate Phase 2 | Status set to In progress. Scale test infrastructure ready. G to run locally: python3 scripts/scale_test.py --discover, then --run-events with chosen IDs. | M9 started | G + Claude (Cowork)
2026-06-01 | M9 — Scale test: 3 events processed | pipeline/analyze/run.py: fixed article lookup to search data/ingested/<beat>/ for live articles. scripts/scale_test.py: --discover and --run-events phases. Ran evt_009 (24 art), evt_068 (6 art), evt_065 (4 art) through full pipeline. All 3 events viewable at localhost:3000. | M9 scale test complete — pipeline end-to-end proven on live data | G + Claude (Cowork)
2026-06-01 | Ingest — concurrent body fetching | pipeline/ingest/rss.py: replaced sequential per-article HTTP fetch (1s global delay) with ThreadPoolExecutor (MAX_CONCURRENT_FETCHES=8) and per-domain rate limiting. Phase 1 collects all RSS entries, Phase 2 fetches bodies concurrently. ~10x speed improvement. | Sequential ingest took ~10min for 400 articles; concurrent takes ~1min | Claude (Cowork)
2026-06-01 | Ingest — RSS fixes (User-Agent, topic_filter, URLs) | pipeline/ingest/rss.py: browser User-Agent added to feedparser calls; topic_filter keyword filtering; rss_fallback support. config/beats/israel_middle_east.json: fixed Jerusalem Post URL, replaced Reuters and i24 with Google News RSS proxy, added topic_filter to Al Jazeera and Euronews, updated Haaretz URL + fallback. | Fixed 5 of 10 sources that were producing 0 articles | Claude (Cowork)
2026-06-01 | Cluster — threshold + time-window constraint | pipeline/cluster/group.py: DEFAULT_THRESHOLD raised 0.50 → 0.70; added time_window_hours parameter (default 48h) that prevents clustering articles published >48h apart; pub_dates wired through cluster/run.py and scale_test.py. | Previous threshold caused 367-article mega-cluster on live beat data; new defaults produce coherent same-day event clusters | Claude (Cowork)
2026-06-01 | Generate — prompt + validation fix | pipeline/generate/generate.py: GENERATE_SYSTEM prompt now explicitly states clm_XXX belongs in claim_ids and src_XXX belongs in source_ids. validate_report() now auto-corrects transposed IDs (moves clm_XXX from source_ids → claim_ids and vice versa) instead of hard-aborting. | evt_009 first run failed with [ERROR] p9: unknown source_id clm_011 — model confused the two ID fields | Claude (Cowork)
2026-06-02 | Beat config — new right sources + domain_map | Added Ynet News (center-right), Arutz Sheva (right), Israel Hayom (right) via Google News RSS proxy. Added domain field to all sources. Added domain_map section for GDELT domain→outlet matching. Beat now covers full left→right spectrum. | Beat previously had no "right" sources; center-right was the rightmost tier | G + Claude (Cowork)
2026-06-02 | GDELT ingest — pipeline/ingest/gdelt.py | New module: queries GDELT DOC 2.0 API (gdeltdoc library) with beat keywords, maps domains to outlet metadata via domain_map, logs unknown domains to data/suggested_sources.json with enrichment/reviewed status tracking. Integrated into ingest/run.py (--no-gdelt flag to skip) and scale_test.py. | RSS feeds are fragile and blocked by many outlets; GDELT surfaces articles from any indexed outlet including bot-blocked ones | Claude (Cowork)
2026-06-02 | Source discovery — suggested_sources.json | Unknown domains from GDELT runs are logged to data/suggested_sources.json with: seen_count, sample_titles, first_seen, enriched (bool), reviewed (bool). Weekly scheduled task (Monday 9am) researches each un-enriched domain via web search and presents a formatted digest for G to review. | At scale, manual source curation needs automated discovery with human approval gate | Claude (Cowork)
2026-06-02 | Weekly scheduled task — newsroom-source-review | Created scheduled task running every Monday at 9am. Reads suggested_sources.json, uses web search to enrich un-enriched domains (bias rating, ownership, funding, country, editorial stance, flags), writes enrichment back to file, presents formatted review digest to G. | G needs periodic notification and context to make informed decisions on new sources | Claude (Cowork)
2026-06-02 | Frontend — force-dynamic rendering | Added export const dynamic = "force-dynamic" to web/app/page.tsx and web/app/event/[id]/page.tsx. Removed generateStaticParams(). New event JSON files now appear in the UI without restarting the dev server. | Next.js was pre-building a static list of event pages at startup; new events added after launch returned 404 | Claude (Cowork)
2026-06-02 | M9 — Scale test: 6 events total processed | Three additional events processed: evt_2026_06_02_044 (18 art, full spectrum), evt_2026_06_02_014 (12 art, left→right), evt_2026_06_02_063 (5 art, high-contrast left vs right). First runs with Arutz Sheva and Israel Hayom in the source set. | Scale test now covers full ideological spectrum including right-wing Israeli sources | G + Claude (Cowork)
2026-06-02 | B-08 — one_sided paragraph kind | Added one_sided as a fifth report paragraph kind. Rewrote generate prompt kind definitions with strict claim-data-driven rules: contested requires contested_by non-empty on cited claims; one_sided covers single-lane coverage. validate_report() now warns when a contested paragraph has no contested claims. Report schema_version bumped 0.1→0.2. | contested was being applied to one-sided coverage, implying active dispute where there was none; one-sided coverage is itself a meaningful signal | G + Claude (Cowork)
2026-06-02 | B-08 — Kind-based paragraph ordering | Replaced Gaza-specific ordering section in GENERATE_SYSTEM (Hamas, ceasefire, territorial expansion, etc.) with kind-based sequence: agreed → background → framing/one_sided → contested. Added explicit rule: omit kind groups that have no supporting claims — never invent paragraphs to fill a slot. | Hardcoded Gaza topic ordering was irrelevant and potentially confusing for non-Gaza events (e.g. evt_065 France-Israel defence ban) | G + Claude (Cowork)
2026-06-02 | Outlet registry — populated + weekly review | Populated data/sources/outlet_provenance.json with all 13 current beat outlets plus name variants (BBC News, The Guardian, Israel Hayom, Ynet News, Arutz Sheva, Middle East Eye, Jerusalem Post, i24 News added). Created scripts/registry_review.py: weekly Haiku-powered ownership check, presents digest, no auto-edits. Created scheduled task newsroom-registry-review (Thursdays 9am). | Most beat outlets had ownership=None in source data, causing empty description boxes in Sources section; outlet ownership can change so needs periodic automated review | G + Claude (Cowork)
2026-06-02 | UI — Sources grouped by outlet (OutletCard) | Created web/components/OutletCard.tsx: groups all articles from the same outlet into one card. Ownership and bias badge shown once. Individual articles (date, author, link) listed within, collapsed behind toggle when multiple. Updated page.tsx sources section to use OutletCard; header now shows outlet count + article count. | Sources section showed one card per article — 4 Israel Hayom cards, 2 Guardian cards with different authors — redundant and hard to scan | G + Claude (Cowork)
2026-06-02 | Handover — HANDOVER_SESSION_9.md | Prepared docs/HANDOVER_SESSION_9.md covering all Session 9 changes, next steps (regenerate evt_065, external validation), scheduled task notes, and updated working conventions. | Session continuity | Claude (Cowork)
2026-06-02 | UI — Transparency toggle fix | Sources/receipts now hidden when transparency toggle is off, even if Show Sources was previously clicked. expanded state persists but receipt only renders when both expanded && transparencyMode. | Receipts were visible after toggling transparency off — G reported | G + Claude (Cowork)
2026-06-02 | UI — Sidebar bar alignment | Restructured layout: each paragraph is now a flex row containing its own bar segment + content. Previously bar was a separate column using flexGrow:1, causing equal-division misalignment. Bar now stretches to match exactly the height of its paragraph. | Sidebar colors were cut off mid-paragraph and misaligned | Claude (Cowork)
2026-06-02 | UI — Contested receipt: ↔ separator | Receipt for contested paragraphs now shows supporting outlets on one side, contesting outlets on the other, separated by ↔. Outlets that appear in both supported_by and contested_by (different articles) are kept on the supporting side with a note. Falls back to plain source list when contested_by is empty. | G reported military operations sources appeared side by side with no visual contention indicator | Claude (Cowork)
2026-06-02 | Data bug — clm_020 (evt_044) | clm_020 classified as contested but contested_by=[]. The reconciler identified an Iran/US dispute within the claim text, but both reporting outlets (BBC, Euronews) agreed on the facts — no outlet contradiction exists. Should be corroborated. Will auto-correct on next pipeline re-run once reconcile.py is patched. Added to backlog as B-09. | Contested paragraph receipt showed no ↔ separator; B-08 validation should have warned | G + Claude (Cowork)
2026-06-02 | M9 — Self-review on evt_044 | G reviewed evt_2026_06_02_044 (18 articles, full spectrum) as centrist validator. Findings: (1) article reads balanced, sources well mixed; (2) contested paragraphs text well written — data bugs noted above; (3) transparency toggle creates anticipation to see sourcing; (4) full outlet range represented with room for each. Formal external validation deferred. | Proceeding with self-review given no external validators currently available | G
2026-06-02 | Scheduled task — registry-review pre-approved | newsroom-registry-review task Run Now triggered manually to pre-approve tool permissions before first automatic Thursday 9am run. | Required once to grant tool access before automated runs | G
2026-06-03 | B-09 — reconcile.py contested_by guard | Added B-09 guard to enforce_classification_rules() in pipeline/analyze/reconcile.py. After B-02 runs (which cleans contested_by), if a claim is classified contested but contested_by is still empty, it is reclassified: corroborated if supported_by spans ≥2 bias tiers, single_source otherwise. Fixes clm_020 (evt_044) and any future reconciler false positives where dispute is inferred from claim text rather than cross-outlet disagreement. | Contested claims with empty contested_by produce a broken receipt UI (no ↔ separator) and mislead the reader into thinking an outlet-level dispute exists when none does | Claude (Cowork)
2026-06-04 | Vercel deployment — next.config.ts + GitHub init | Added outputFileTracingIncludes to web/next.config.ts so Vercel bundles data/events/**/* in the serverless function. Initialised git repo, pushed to GitHub (Ephemiral/Newsroom). Deployed to Vercel; permanent public URL available for external validators. | localtunnel was unreliable; reviewers needed a stable URL that works without keeping a laptop running | G + Claude (Cowork)
2026-06-04 | Generate — JSON parse robustness fix | Rewrote _parse_response() in pipeline/generate/generate.py to match extract.py: strips markdown fences, repairs truncated output (stop_reason==max_tokens), falls back to json_repair library. Previously used bare json.loads() which crashed on minor model output malformation. | First scale test run failed with JSONDecodeError on evt_014 generate stage | Claude (Cowork)
2026-06-04 | Scale test — 3 new events processed | Ran evt_2026_06_04_014 (Israel Day Parade/Smotrich, 17 art), evt_2026_06_04_062 (US-Iran ceasefire, 23 art), evt_2026_06_04_066 (Iranian drone/Kuwait, 12 art) through full pipeline. Total events: 9. All viewable at newsroom-sand-seven.vercel.app. | M9 scale target is 20-30 events; now at 9 | G + Claude (Cowork)
2026-06-04 | B-10/B-11 — Generate stage kind enforcement | Two bugs identified and fixed in pipeline/generate/generate.py: (1) B-10: model was returning claim_ids:[] in all paragraph supports, breaking downstream validation. (2) B-11: model labelled paragraphs kind=contested based on topic dispute rather than outlet-level disagreement. Fix: added ⚠ CONTESTED_BY STATUS header in _build_claims_block() when no claims have contested_by populated; added _enforce_paragraph_kinds() post-generation guard that reclassifies contested→framing when no cited claim has contested_by non-empty (or claim_ids is empty). Logged as B-10/B-11 in Master Doc §13. | evt_062 had 0 outlet-level disputes yet 4 contested paragraphs — readers were misled | G + Claude (Cowork)